## Story Tracker
Databricks Unity Catalog — Masking Policy Implementation Tracker
Project: Redshift → Unity Catalog Migration |  |  |  | Paulam Basu (Lead) ¦ Balaji (Dev) ¦ Scott (Architect) ¦ Nathan ¦ Rahul ¦ DG/Governance |  |  |  |  | Last Updated: April 01, 2026
🟣 DG Requirement |  | 🟢 Pilot Story |  | 🔵 Impl Story |  | 🔴 High 🟠 Medium
Story ID | Type | Story Title | Priority | Owner | Collaborators | Depends On | Blocks | Sprint | Pts | Start Date | Target Date | Status | Notes
DG-001 | DG Req | Finalize Masking Requirements – Hashing for Joinable Fields | High | Nathan | Paulam Basu, Scott |  | MP-001,MP-002,MP-003 | Sprint 1 | 3 | 2025-04-07 | 2025-04-17 | Not Started | Action item: Nathan. Distinguish joinable (hash) vs non-joinable (mask) vs free-text (redact-all)
DG-002 | DG Req | Confirm DG Metadata Catalog Ownership & Access Model | High | Governance | Paulam Basu |  | MP-001,MP-004 | Sprint 1 | 3 | 2025-04-07 | 2025-04-17 | Not Started | Action item: Governance. Functions/tags owned centrally in DG catalog; engineers tag only
DG-003 | DG Req | Test Auto-Classification for Free-Text Field Tagging | Medium | Rahul | Governance |  | MP-003 | Sprint 1 | 5 | 2025-04-07 | 2025-04-21 | Not Started | Action item: Rahul/Governance. Validate redact-all triggers on auto-classified free-text cols
DG-004 | DG Req | Review Hashing Strength – Salting with Security/ITRC | High | Rahul | Scott |  | MP-002 | Sprint 1 | 3 | 2025-04-07 | 2025-04-17 | Not Started | Action item: Rahul/Scott. Determine salting requirement and approved hashing algorithm
PILOT-001 | Pilot | Pilot: Single Column Masking End-to-End (Function→Tag→Policy) | High | Paulam Basu | Balaji, Scott | DG-001,DG-002 | DG-REVIEW-001 | Sprint 2 | 8 | 2025-04-21 | 2025-05-05 | Not Started | Action item: Paulam/Scott/Alok. ONE column (e.g. email). Full pattern: function→tag→policy. Balaji implements
DG-REVIEW-001 | DG Req | DG Review & Sign-off on Pilot Column Masking | High | Governance | Paulam Basu, Scott | PILOT-001 | MP-005 | Sprint 2 | 2 | 2025-05-05 | 2025-05-12 | Not Started | Gate: DG must sign off on pilot before full rollout. Validates pattern, hash output, policy binding
MP-001 | Story | PII Column Inventory & Classification (All Tables) | High | Paulam Basu | Balaji | DG-001,DG-002 | MP-002,MP-003 | Sprint 2 | 5 | 2025-04-21 | 2025-04-28 | Not Started | Engineers tag columns only; DG owns functions centrally per DG-002
MP-002 | Story | Deterministic Hashing Functions – Joinable Fields (SSN, Email) | High | Balaji | Paulam Basu | DG-001,DG-004,MP-001 | MP-004 | Sprint 3 | 5 | 2025-05-05 | 2025-05-12 | Not Started | Full deterministic hash only — no partial reveal. Salt per DG-004 approval
MP-003 | Story | Masking & Redact-All Functions – Non-Joinable & Free-Text Fields | High | Balaji | Paulam Basu | DG-001,DG-003,MP-001 | MP-004 | Sprint 3 | 5 | 2025-05-05 | 2025-05-12 | Not Started | Single redact-all for free-text; standard mask for non-joinable PII
MP-004 | Story | ABAC Tag-Driven Policy Binding (Per Catalog) | High | Paulam Basu | Balaji | DG-002,MP-002,MP-003 | MP-005 | Sprint 3 | 8 | 2025-05-12 | 2025-05-26 | Not Started | Pattern: Function + Tag + Policy per catalog. ALTER TABLE ... SET MASK bindings
MP-005 | Story | Full PII Column Masking Rollout – All Tables | High | Balaji | Paulam Basu | DG-REVIEW-001,MP-004 | MP-006,MP-007 | Sprint 4 | 8 | 2025-05-26 | 2025-06-09 | Not Started | Unlocked only after DG-REVIEW-001 pilot sign-off. Full rollout across all PII columns
MP-006 | Story | Join Correctness Validation – Hashed Joinable Fields | High | Paulam Basu | Balaji | MP-005 | MP-008 | Sprint 4 | 8 | 2025-06-02 | 2025-06-16 | Not Started | Validate consistent hash enables correct downstream joins. Pre/post reconciliation
MP-007 | Story | Role & Group Mapping – Masking Exemptions & S3 Access Disable | Medium | Balaji | Paulam Basu, DG Team | MP-005 | MP-008 | Sprint 4 | 5 | 2025-06-02 | 2025-06-09 | Not Started | UC groups + disable direct S3 access; all access via Unity Catalog only
MP-008 | Story | DLT Pipeline Masking Validation | Medium | Balaji | Paulam Basu | MP-006,MP-007 | MP-009 | Sprint 4 | 5 | 2025-06-09 | 2025-06-16 | Not Started | DLT-Meta pipelines respect UC masking; silver/gold views validated
MP-009 | Story | DABs Packaging for Multi-Environment Deployment | Medium | Balaji | Paulam Basu, Scott | MP-008 | MP-010 | Sprint 5 | 5 | 2025-06-16 | 2025-06-23 | Not Started | Bundle masking functions + policies for dev/qa/prod; Scott arch review
MP-010 | Story | Audit Logging & system.access Dashboard | Medium | Paulam Basu | Balaji, DG Team | MP-005 | MP-011 | Sprint 5 | 8 | 2025-06-16 | 2025-06-30 | Not Started | Lakeview: hash vs mask vs bypass ratio, PII access events, anomaly alerts
MP-011 | Story | Team Working Session – Iterate & Scale Across Datasets | Medium | Paulam Basu | All | MP-009,MP-010 | MP-012 | Sprint 5 | 3 | 2025-06-30 | 2025-07-07 | Not Started | Recurring session. Align hashing vs masking decisions consistently across all datasets
MP-012 | Story | UAT & Data Governance Final Sign-off | High | Governance | Scott, Paulam Basu, Balaji | MP-011 |  | Sprint 5 | 3 | 2025-07-07 | 2025-07-14 | Not Started | Full UAT: joinable/non-joinable/free-text types, all roles. Scott arch sign-off
TRACKER SUMMARY
Total Stories |  | Total Story Points |  | DG Req Stories |  | Pilot Stories |  | Impl Stories |  | Not Started |  | In Progress |  | Blocked
18 |  | 92 |  | 5 |  | 1 |  | 12 |  | 18 |  | 0 |  | 0

## Dependency Map
Story Dependency Map — Masking Policy Implementation
Story ID | Story Title | Type | Depends On (must complete first) | Blocks (unblocks these) | Owner
DG-001 | Finalize Masking Requirements | DG Req | — (No dependency) | MP-001, MP-002, MP-003 | Nathan
DG-002 | Confirm DG Metadata Catalog Ownership | DG Req | — (No dependency) | MP-001, MP-004 | Governance
DG-003 | Test Auto-Classification Free-Text Tagging | DG Req | — (No dependency) | MP-003 | Rahul
DG-004 | Review Hashing Strength – Salting | DG Req | — (No dependency) | MP-002 | Rahul / Scott
PILOT-001 | Pilot: Single Column End-to-End | Pilot | DG-001, DG-002 | DG-REVIEW-001 | Paulam Basu / Balaji
DG-REVIEW-001 | DG Review & Sign-off on Pilot | DG Req | PILOT-001 | MP-005 (full rollout gate) | Governance
MP-001 | PII Column Inventory & Classification | Story | DG-001, DG-002 | MP-002, MP-003 | Paulam Basu
MP-002 | Deterministic Hashing – Joinable Fields | Story | DG-001, DG-004, MP-001 | MP-004 | Balaji
MP-003 | Masking & Redact-All – Non-Joinable/Free-Text | Story | DG-001, DG-003, MP-001 | MP-004 | Balaji
MP-004 | ABAC Tag-Driven Policy Binding | Story | DG-002, MP-002, MP-003 | MP-005 | Paulam Basu
MP-005 | Full PII Rollout – All Tables | Story | DG-REVIEW-001, MP-004 | MP-006, MP-007 | Balaji
MP-006 | Join Correctness Validation | Story | MP-005 | MP-008 | Paulam Basu
MP-007 | Role & Group Mapping + S3 Access Disable | Story | MP-005 | MP-008 | Balaji
MP-008 | DLT Pipeline Masking Validation | Story | MP-006, MP-007 | MP-009 | Balaji
MP-009 | DABs Multi-Env Deployment | Story | MP-008 | MP-010 | Balaji
MP-010 | Audit Logging & system.access Dashboard | Story | MP-005 | MP-011 | Paulam Basu
MP-011 | Team Working Session – Iterate & Scale | Story | MP-009, MP-010 | MP-012 | Paulam Basu
MP-012 | UAT & DG Final Sign-off | Story | MP-011 | — (Final story) | Governance

## Action Items
Action Items from Meeting — Masking Policy
# | Action Item | Owner | Linked Story | Status
1 | Update and share final masking requirements (hashing for joinable fields) | Nathan | DG-001 | Open
2 | Pilot one PII field end-to-end: function → tag → policy | Paulam / Scott / Alok | PILOT-001 | Open
3 | Confirm DG metadata catalog ownership and access model | Governance | DG-002 | Open
4 | Test auto-classification, especially free-text tagging | Rahul / Governance | DG-003 | Open
5 | Review hashing strength (salting) with Security/ITRC | Rahul / Scott | DG-004 | Open
6 | Set recurring working session to iterate and scale | Team | MP-011 | Open